Name: rita

Matricule No: biylt87i

School: gygkh

Department: Computer Science

Level: Level 100

To analyze the project schedule and determine the necessary parameters for the sponsor, the activities, predecessors, and durations must first be established. Assuming a typical project structure for network infrastructure development, the following data is used (durations are provided in weeks):

| Activity | Description | Predecessor(s) | Duration (D) (Weeks) |
| --- | --- | --- | --- |
| A | Planning & Requirements | - | 3 |
| B | Site Survey & Acquisition | - | 4 |
| C | Equipment Procurement | A | 6 |
| D | Fiber Optic Design | A | 2 |
| E | Trenching & Conduit Install | B | 8 |
| F | Fiber Laying & Splicing | C, E | 5 |
| G | Network Configuration | D, F | 3 |
| H | Testing & Acceptance | G | 2 |

### 1. CPM Analysis (Early Start/Finish, Late Start/Finish, Slack)

The following table outlines the Critical Path Method (CPM) calculations used to determine scheduling flexibility and resource prioritization:

| Activity | D | ES | EF | LS | LF | Slack (LS-ES) | Critical? |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | 3 | 0 | 3 | 3 | 6 | 3 | No |
| B | 4 | 0 | 4 | 0 | 4 | 0 | Yes |
| C | 6 | 3 | 9 | 6 | 12 | 3 | No |
| D | 2 | 3 | 5 | 15 | 17 | 12 | No |
| E | 8 | 4 | 12 | 4 | 12 | 0 | Yes |
| F | 5 | 12 | 17 | 12 | 17 | 0 | Yes |
| G | 3 | 17 | 20 | 17 | 20 | 0 | Yes |
| H | 2 | 20 | 22 | 20 | 22 | 0 | Yes |

### 2. Network Diagram (Activity-on-Node)

The project network structure, modeled using the Activity-on-Node (AON) convention, guides management on dependencies and workflow.

(Start) ---> A(3) ---> C(6) ---\

(Start) ---> B(4) ---> E(8) ---> F(5) ---> G(3) ---> H(2) ---> (End)

\---> D(2) ---/

Note: F is dependent on both C and E. G is dependent on both D and F.

### 3. Gantt Chart of the Activities

This visualization shows the earliest possible scheduling for each activity and highlights the critical path tasks (marked with '*'). The timeline is represented in weeks (0 to 22).

Activity | 0 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 |

---------|---|---|---|---|---|---|---|---|---|---|---|---|

A        |XXX|   |   |   |   |   |   |   |   |   |   |   |

B*       |XXXXX|   |   |   |   |   |   |   |   |   |   |   |

C        |   |XXX|XXX|XXX|   |   |   |   |   |   |   |   |

D        |   |XXX|   |   |   |   |   |   |   |   |   |   |

E*       |   |   |XXXXXXX|XXXXXXX|XXXXXXX|   |   |   |   |   |

F*       |   |   |   |   |   |   |XXXXXXX|XXX|   |   |   |   |

G*       |   |   |   |   |   |   |   |   |XXXXXXX|   |   |   |

H*       |   |   |   |   |   |   |   |   |   |XXXXX|   |   |

### 4. Determination of the Critical Path and Project Duration

Critical Path of the Project:

The critical path comprises the sequence of activities that have zero slack, meaning any delay in these activities will result in a delay in the overall project completion. The identified critical path is:

B -> E -> F -> G -> H

Shortest Project Completion Time:

The shortest time required to complete the project, based on the accumulated duration of the critical path, is 22 weeks. This value is determined by the Earliest Finish (EF) time of the terminal activity (H).

### 5. Limitations of the Critical Path Method (CPM)

While CPM is a robust deterministic scheduling tool foundational to project management, its utility is constrained by several real-world assumptions, particularly critical in large-scale technical projects like network construction:

1.  Fixed Activity Durations: CPM operates under the assumption that the duration of each activity is known precisely and fixed. It does not account for the inherent variability and uncertainty common in infrastructure projects, such as unforeseen permitting issues, weather delays, or supply chain volatility. This limitation makes the deterministic result of 22 weeks a best-case estimate, rather than a probabilistic outcome.

2.  Resource Overload Neglect: The standard CPM analysis assumes that unlimited resources are available or, at least, that resources are sufficient to allow tasks to start at their earliest possible time. It fails to account for resource constraints (e.g., a limited number of specialized splicing crews or engineers) which might necessitate rescheduling non-critical activities, potentially shifting the critical path itself. Resource leveling is typically required as a separate step.

3.  Dependency Flexibility: CPM relies strictly on well-defined 'Finish-to-Start' (FS) dependencies. In complex projects, 'Start-to-Start' (SS) or 'Finish-to-Finish' (FF) dependencies might be more realistic, and the rigid application of standard CPM may oversimplify concurrent work opportunities.

4.  No Learning Curve or Efficiency Modeling: CPM treats the performance rate as constant. It does not model how productivity might increase with experience (learning curve effects) or decrease due to fatigue or multi-tasking interference, which is highly relevant in multi-week technical installations.