Name: rita

Matricule No: hczuye

School: buer

Department: Computer Science

Level: Level 100

The project involves establishing a communications network between two communities. Based on the documented activities, durations, and precedence relationships, a Critical Path Method (CPM) analysis was executed to optimize the implementation timeline.

### Project Schedule and CPM Analysis

The following table outlines the temporal metrics derived from the Forward Pass (Early Start/Finish) and Backward Pass (Late Start/Finish) calculations necessary for determining slack and identifying critical activities. Durations are measured in weeks.

| Activity | Duration | Predecessor | ES | EF | LS | LF | Slack | Critical Path |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A (Survey & Planning) | 4 | - | 0 | 4 | 4 | 8 | 4 | No |
| B (Land Rights & Approvals) | 6 | - | 0 | 6 | 0 | 6 | 0 | Yes |
| C (Hardware Procurement) | 8 | A | 4 | 12 | 8 | 16 | 4 | No |
| D (Trenching & Conduit) | 10 | B | 6 | 16 | 6 | 16 | 0 | Yes |
| E (Civil Infrastructure Setup) | 5 | C, D | 16 | 21 | 16 | 21 | 0 | Yes |
| F (Fiber Installation/Pulling) | 12 | D | 16 | 28 | 16 | 28 | 0 | Yes |
| G (Network Equipment Config) | 7 | E | 21 | 28 | 21 | 28 | 0 | Yes |
| H (System Integration/Testing) | 3 | F, G | 28 | 31 | 28 | 31 | 0 | Yes |

(ES = Early Start, EF = Early Finish, LS = Late Start, LF = Late Finish)

### 1. Gantt Chart of Activities

This visualization illustrates the planned timeline for each activity, highlighting the critical activities that dictate the project's overall duration.

| Week | 0-4 | 4-8 | 8-12 | 12-16 | 16-20 | 20-24 | 24-28 | 28-31 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A (4 weeks) | XXXX | .... | .... | .... | .... | .... | .... | .... |
| B (6 weeks) | XXXXXX | .... | .... | .... | .... | .... | .... | .... |
| C (8 weeks) | .... | XXXX | XXXX | .... | .... | .... | .... | .... |
| D (10 weeks) | .... | .... | .... | XXXX | XXXXXX | .... | .... | .... |
| E (5 weeks) | .... | .... | .... | .... | XXXXX | .... | .... | .... |
| F (12 weeks) | .... | .... | .... | .... | XXXX | XXXX | XXXX | .... |
| G (7 weeks) | .... | .... | .... | .... | .... | XXXXXX | X | .... |
| H (3 weeks) | .... | .... | .... | .... | .... | .... | .... | XXX |

(Note: 'X' indicates activity duration. Critical activities (B, D, E, F, G, H) must finish precisely on schedule.)

### 2. Network Diagram (Activity-on-Node AON)

The diagram depicts the required workflow and dependencies for the project implementation. Each node represents an activity, and arrows indicate mandatory precedence relationships.

1. Start Node connects to A and B.

2. A connects to C.

3. B connects to D.

4. C and D both connect to E (Merge Point).

5. D also connects to F (Split Point).

6. E connects to G.

7. F and G both connect to H (Final Merge Point).

8. H connects to the Finish Node.

### 3. Determination of the Critical Path

The Critical Path (CP) comprises the sequence of activities that have zero slack, meaning any delay in these activities will directly delay the entire project completion. Analyzing the schedule reveals two distinct paths sharing the longest duration of 31 weeks.

Critical Path 1: B -> D -> E -> G -> H

(Duration: 6 + 10 + 5 + 7 + 3 = 31 weeks)

Critical Path 2: B -> D -> F -> H

(Duration: 6 + 10 + 12 + 3 = 31 weeks)

### 4. Project Completion Time (Shortest Time)

The shortest time required to complete the project is equal to the duration of the critical path.

Project Completion Time: 31 Weeks

### 5. Limitations of the Critical Path Method (CPM)

While CPM is a powerful deterministic tool for scheduling, several inherent limitations must be considered by management:

1.  Fixed Time Estimates: CPM assumes that activity durations are known and fixed (deterministic). In reality, project times are often probabilistic, subject to variations, procurement issues, or unforeseen environmental factors, which PERT (Program Evaluation and Review Technique) is better equipped to handle.

2.  Lack of Resource Constraints: Standard CPM calculations do not natively incorporate resource availability. It is possible that the schedule defined by the CP requires resources (personnel, specialized equipment) that are simultaneously needed by multiple activities, necessitating manual resource leveling outside of the initial CPM output.

3.  Complexity for Large Projects: As the number of activities and interdependencies grows, manually updating and analyzing the CPM network becomes cumbersome and prone to error.

4.  Fixed Precedence Relationships: The method assumes that the sequence of activities is strictly defined and cannot be altered, potentially limiting flexibility in execution.